## NRM2 BOQ
Bill of Quantities: Brown Hazel
Item | Description | Qty | Unit | Rate | Total
General Preliminaries
1 | Provide site foreman/supervisor including management of workers, scheduling, health and safety, coordination of works and overheads for the duration of the project. | 1 | each | 7000 | 7000
2 | Supply and display project sign boards including company name, project information and health and safety signage. | 1 | each | 125 | 125
3 | Carry out cleaning of site and works including removal of debris, sweeping, and maintaining clean working areas as per client requirements. | 1 | each | 800 | 800
4 | Provide health and safety measures including PPE, first aid facilities, safety signage and compliance with regulations. | 1 | each | 337.5 | 337.5
5 | Provide waste management including skips, loading waste, disposal at licensed facility and keeping site tidy. | 10 | each | 318.75 | 3187.5
Fences and Barriers
6 | Hire and erect temporary Heras fencing panels including clips, concrete feet and vehicle/pedestrian gates for site security and removal on completion. | 105.3 | m | 87.02 | 9163.1
Site Equipment
7 | Supply and maintain site storage container including delivery, hire and removal. | 1 | each | 1137.5 | 1137.5
8 | Supply and maintain site toilet facilities including cleaning and consumables for the duration of works. | 1 | each | 1181.25 | 1181.25
Demolition / Removal
9 | Carry out demolition and removal of existing structures or elements including temporary supports, breaking out, loading to skips, disposal off-site and making good adjacent finishes. | 1 | each | 7376.25 | 7376.25
Scaffolding
10 | Provide static scaffolding including design, erection, hire, inspection, adaption and dismantling to provide safe access for trades to working areas. | 1 | each | 9504 | 9504
SVP
11 | Supply and install soil pipes and fittings including connection to existing drainage system, fixings and testing. | 1 | each | 211.23 | 211.23
Surface Water Manhole
12 | Supply and place clean pea gravel bedding and surround to drainage pipes and soakaway crates. | 0.7 | m3 | 273.36 | 180.5
13 | Load and cart away surplus excavated soil from site to a licensed tip as required. | 1 | m3 | 211.25 | 219.36
14 | Supply and install inspection chambers and covers including bases, shafts, frames and lids complete. | 2 | each | 267.75 | 535.5
15 | Excavate trenches to required depth and width for drainage runs including support of sides, removal of spoil and preparation of base. | 0.9 | m3 | 153.42 | 130.59
Surface Water Drainage run
16 | Supply and lay PVC-U drainage pipes and fittings including couplers, bends, junctions and testing. | 1 | each | 660.29 | 660.29
17 | Supply and place clean pea gravel bedding and surround to drainage pipes or soakaways. | 3 | m3 | 217.86 | 650.3
18 | Excavate trenches to required depth and width for drainage runs including support of sides, removal of spoil and preparation of base. | 7.9 | m3 | 114.68 | 903.09
19 | Load and cart away surplus excavated soil from site to a licensed tip as required. | 4 | m3 | 90.21 | 358.23
20 | Backfill excavations and trenches with selected excavated material or imported fill, compacted in layers. | 4.6 | m3 | 57.6 | 266.11
Aco Channels
21 | Load and cart away surplus excavated soil from site to a licensed tip as required. | 0.4 | m3 | 398.94 | 175.21
22 | Supply and lay PVC-U drainage pipes and fittings including couplers, bends, junctions and testing. | 1 | each | 473.38 | 473.38
23 | Provide and place concrete bedding and haunching to drainage channels and pipes including formwork as necessary. | 0.3 | m3 | 525.48 | 151.34
24 | Excavate trenches to required depth and width for drainage runs including support of sides, removal of spoil and preparation of base. | 0.4 | m3 | 124.76 | 44.91
25 | Supply and install linear drainage channels with gratings and required connections to drainage system. | 6 | m | 22.7 | 136.2
Soakaway
26 | Backfill excavations and trenches with selected excavated material or imported fill, compacted in layers. | 0.8 | m3 | 57.94 | 48.96
27 | Load and cart away surplus excavated soil from site to a licensed tip as required. | 2.7 | m3 | 107.87 | 289.13
28 | Supply and install modular plastic soakaway crates wrapped in geotextile fabric to form soakaway including excavation and connections. | 2.2 | m3 | 218.71 | 480.51
29 | Supply and lay geotextile membrane around soakaway crates or under permeable paving as specified. | 11.7 | m2 | 5.19 | 60.56
30 | Excavate trenches to required depth and width for drainage runs including support of sides, removal of spoil and preparation of base. | 3 | m3 | 112.55 | 342.39
Strip Foundation
31 | Supply and place in-situ concrete to foundations or slabs including mixing, transport, laying, compacting and curing. | 8.9 | m3 | 205.61 | 1821.28
32 | Excavate for foundations, footings or slabs to required levels including removal of spoil, support of sides and keeping excavations free of water. | 26.6 | m3 | 72.86 | 1936.19
33 | Load and cart away surplus excavated soil from site to a licensed tip as required. | 32.4 | m3 | 70.31 | 2279.28
Trench Foundation (Historic Septic Tank Area)
34 | Supply and place in-situ concrete to foundations or slabs including mixing, transport, laying, compacting and curing. | 4.5 | m3 | 250.06 | 1125.25
35 | Excavate for foundations, footings or slabs to required levels including removal of spoil, support of sides and keeping excavations free of water. | 6 | m3 | 82.24 | 493.44
36 | Load and cart away surplus excavated soil from site to a licensed tip as required. | 7.3 | m3 | 106.34 | 778.38
Cavity Walls Below DPC
37 | Provide and place concrete infill or blinding including levelling and compaction. | 1.7 | m3 | 450.14 | 744.41
38 | Construct inner skin of cavity walls using blockwork including mortar, ties and coordination with outer skin. | 34.3 | m2 | 76 | 2606.93
39 | Supply and lay damp-proof course to walls including laps and sealing at junctions. | 98 | m | 4.3 | 421.4
40 | Construct outer skin of cavity walls using facing brick or block including mortar, ties and joint finishes. | 34.3 | m2 | 111.09 | 3810.45
Concrete Floor
41 | Supply and lay sand/cement floor screed including placing, levelling and finishing to receive floor coverings. | 85.5 | m2 | 35.63 | 3046.71
42 | Supply and compact hardcore fill material to required thickness as sub-base under slabs or paving. | 12.8 | m3 | 257.64 | 3304.19
43 | Provide protective screed or layer over insulation or membranes to protect during subsequent works. | 93.8 | m2 | 3.4 | 319.04
44 | Construct in-situ concrete slab including reinforcement, placing, compaction, finishing and curing. | 12.8 | m3 | 224.41 | 2878.03
45 | Excavate to reduce ground levels to formation including disposal of surplus material and trimming to level. | 33.8 | m3 | 74.35 | 2510.85
46 | Supply and install perimeter insulation to floor slab edges to reduce cold bridging. | 8.3 | m2 | 10.47 | 87.13
47 | Load and cart away surplus excavated soil from site to a licensed tip as required. | 41.2 | m3 | 64.97 | 2677.05
48 | Supply and install rigid or quilt insulation to floors, walls or roofs to achieve specified thermal performance. | 85.5 | m2 | 19.6 | 1675.5
49 | Provide sand blinding to protect damp proof membranes and provide smooth bedding layer. | 4.3 | m3 | 277.59 | 1186.7
50 | Supply and lay damp proof membrane over hardcore or insulation with laps and sealed joints. | 96.6 | m2 | 2.81 | 271.24
51 | Provide surface finish to concrete slab including trowelling, brushing or power floating to specified finish. | 85.5 | m2 | 4.5 | 384.75
Cavity Wall
52 | Finish wall surfaces with plaster, skim coat or render ready for decoration. | 206 | m2 | 46.92 | 9665.76
53 | Provide wall accessories such as beads, trims or corner protection during finishing of walls. | 51 | each | 8.12 | 414.36
54 | Construct main structural wall skin using blockwork including mortar, ties and coordination with other elements. | 206 | m2 | 57.44 | 11832
55 | Construct outer skin of cavity walls using facing brick or block including mortar, ties and joint finishes. | 206 | m2 | 118.38 | 24385.29
56 | Supply and place insulation within cavity walls to achieve specified thermal performance. | 206 | m2 | 33.9 | 6982.44
Block Wall
57 | Provide general labourers for site tasks including material handling, site cleaning, assisting trades, and miscellaneous labour as required. | 1 | each | 1600 | 1600
58 | Construct solid masonry wall using blockwork including mortar joints and finishes. | 58.5 | m2 | 57.91 | 3388.01
59 | Provide wall accessories such as beads, trims or corner protection during finishing of walls. | 54 | each | 8.26 | 445.93
60 | Finish wall surfaces with plaster, skim coat or render ready for decoration. | 117 | m2 | 26.25 | 3071.71
Timber Stud Wall
61 | Construct timber or metal stud partitions including sole and head plates, studs, noggings, insulation and plasterboard lining. | 77.8 | m2 | 42.31 | 3289.44
62 | Supply and install rigid or quilt insulation to floors, walls or roofs to achieve specified thermal performance. | 77.8 | m2 | 15.3 | 1189.38
63 | Supply and fix plasterboard or lining boards to internal faces of walls including jointing and finishing. | 77.8 | m2 | 24.77 | 1926.22
64 | Finish wall surfaces with plaster, skim coat or render ready for decoration. | 155.5 | m2 | 24.31 | 3780.65
Window Type 1
65 | Supply and install uPVC or aluminium windows including frames, ironmongery, glazing and perimeter sealing. | 1 | each | 600.09 | 600.09
66 | Supply and install insulated cavity closers around window or door openings including fixings. | 5.6 | m | 15.92 | 88.74
67 | Supply and install precast concrete or steel lintels over openings including bearings and installation. | 1 | each | 152.46 | 152.46
68 | Supply and install trickle vents in window frames to provide background ventilation. | 1 | each | 18.63 | 18.63
Window Type 2
69 | Supply and install uPVC or aluminium windows including frames, ironmongery, glazing and perimeter sealing. | 1 | each | 336.55 | 336.55
70 | Supply and install insulated cavity closers around window or door openings including fixings. | 2.7 | m | 21.01 | 56.95
71 | Supply and install precast concrete or steel lintels over openings including bearings and installation. | 1 | each | 127.05 | 127.05
72 | Supply and install trickle vents in window frames to provide background ventilation. | 1 | each | 18.63 | 18.63
Window Type 3
73 | Supply and install uPVC or aluminium windows including frames, ironmongery, glazing and perimeter sealing. | 1 | each | 338.72 | 338.72
74 | Supply and install insulated cavity closers around window or door openings including fixings. | 3.1 | m | 19.16 | 59.1
75 | Supply and install precast concrete or steel lintels over openings including bearings and installation. | 1 | each | 88.56 | 88.56
76 | Supply and install trickle vents in window frames to provide background ventilation. | 1 | each | 18.63 | 18.63
Window Type 4
77 | Supply and install uPVC or aluminium windows including frames, ironmongery, glazing and perimeter sealing. | 1 | each | 420.36 | 420.36
78 | Supply and install insulated cavity closers around window or door openings including fixings. | 3.6 | m | 17.06 | 62.28
79 | Supply and install precast concrete or steel lintels over openings including bearings and installation. | 1 | each | 152.46 | 152.46
80 | Supply and install trickle vents in window frames to provide background ventilation. | 1 | each | 18.63 | 18.63
Window Type 5
81 | Supply and install uPVC or aluminium windows including frames, ironmongery, glazing and perimeter sealing. | 2 | each | 508.96 | 1017.92
82 | Supply and install insulated cavity closers around window or door openings including fixings. | 6.6 | m | 14.33 | 94.57
83 | Supply and install precast concrete or steel lintels over openings including bearings and installation. | 2 | each | 152.46 | 304.92
84 | Supply and install trickle vents in window frames to provide background ventilation. | 2 | each | 18.63 | 37.25
Window Type 6
85 | Supply and install uPVC or aluminium windows including frames, ironmongery, glazing and perimeter sealing. | 2 | each | 389.75 | 779.5
86 | Supply and install insulated cavity closers around window or door openings including fixings. | 4.8 | m | 14.33 | 68.79
87 | Supply and install precast concrete or steel lintels over openings including bearings and installation. | 2 | each | 77.01 | 154.02
88 | Supply and install trickle vents in window frames to provide background ventilation. | 2 | each | 18.63 | 37.25
Window Type 7
89 | Supply and install uPVC or aluminium windows including frames, ironmongery, glazing and perimeter sealing. | 1 | each | 438.79 | 438.79
90 | Supply and install insulated cavity closers around window or door openings including fixings. | 4.8 | m | 14.38 | 68.68
91 | Supply and install precast concrete or steel lintels over openings including bearings and installation. | 1 | each | 77.01 | 77.01
92 | Supply and install trickle vents in window frames to provide background ventilation. | 1 | each | 18.63 | 18.63
Window Type 8
93 | Supply and install uPVC or aluminium windows including frames, ironmongery, glazing and perimeter sealing. | 1 | each | 392.84 | 392.84
94 | Supply and install insulated cavity closers around window or door openings including fixings. | 3 | m | 19.53 | 58.59
95 | Supply and install precast concrete or steel lintels over openings including bearings and installation. | 1 | each | 101.64 | 101.64
96 | Supply and install trickle vents in window frames to provide background ventilation. | 1 | each | 18.63 | 18.63
Window Type 9
97 | Supply and install uPVC or aluminium windows including frames, ironmongery, glazing and perimeter sealing. | 1 | each | 388.35 | 388.35
98 | Supply and install insulated cavity closers around window or door openings including fixings. | 4.6 | m | 14.71 | 67.65
99 | Supply and install precast concrete or steel lintels over openings including bearings and installation. | 1 | each | 77.01 | 77.01
100 | Supply and install trickle vents in window frames to provide background ventilation. | 1 | each | 18.63 | 18.63
Bifold Door
101 | Supply and install insulated cavity closers around window or door openings including fixings. | 4.2 | m | 15.57 | 65.39
102 | Supply and install precast concrete or steel lintels over openings including bearings and installation. | 1 | each | 1206.34 | 1206.34
103 | Supply and install uPVC bifold door set including frame, glazing, ironmongery and weather seals. | 1 | each | 4625.81 | 4625.81
Composite Door
104 | Supply and install composite external door including frame, locks, hinges, seals and threshold. | 1 | each | 1015.25 | 1015.25
105 | Supply and install insulated cavity closers around window or door openings including fixings. | 4.2 | m | 15.57 | 65.39
106 | Supply and install precast concrete or steel lintels over openings including bearings and installation. | 1 | each | 127.05 | 127.05
Wooden Door
107 | Supply and install timber internal or external door including frame, ironmongery and finishing. | 2 | each | 641.08 | 1282.15
108 | Decorate surfaces including filling, sanding, priming and applying paints, stains or finishes as specified. | 7.7 | m2 | 25.62 | 197.5
109 | Supply and install insulated cavity closers around window or door openings including fixings. | 8.4 | m | 14.33 | 120.36
110 | Supply and install precast concrete or steel lintels over openings including bearings and installation. | 2 | each | 127.05 | 254.1
Universal Column
111 | Supply and install structural steel beams including fabrication, delivery, craneage, positioning and bolted connections. | 1 | each | 3230.7 | 3230.7
112 | Supply and install padstones or spreader blocks to support structural steel members. | 4 | each | 71.73 | 286.91
113 | Provide fire protection to structural steel members using intumescent coatings, board encasement or fire-rated linings. | 21.2 | m2 | 24.6 | 521.17
114 | Apply protective paint finish to structural steelwork including preparation and application of primer and top coats. | 21.2 | m2 | 6.53 | 138.35
Connection
115 | Supply and install steel connections including plates, bolts and welds for joints in structural steelwork. | 2 | each | 156.25 | 312.5
116 | Supply and fix bolts, anchors and other fixings associated with installation of structural steelwork or metalwork. | 12 | each | 1.06 | 12.75
Floor
117 | Provide strutting between joists to prevent buckling and spread loads, including noggins and fixings. | 60 | m | 6.74 | 404.51
118 | Supply and install restraint straps to tie walls, floors and roofs together and resist lateral forces. | 2 | each | 24.13 | 48.26
119 | Supply and install rigid or quilt insulation to floors, walls or roofs to achieve specified thermal performance. | 74.3 | m2 | 23.48 | 1745.2
120 | Supply and install structural floor decking or floorboards fixed to joists ready to receive finishes. | 74.3 | m2 | 26.35 | 1958.78
121 | Supply and fix timber floor joists including hangers, connectors and strutting as required. | 226.8 | m | 19.13 | 4339.77
Apex Roof (Main Roof)
122 | Supply and fix collar ties or ties between rafters to provide stability. | 78 | m | 7.12 | 555.08
123 | Supply and fix roof rafters including birdsmouth cuts, fixings to wall plates and ridge. | 354 | m | 8.19 | 2898.47
124 | Supply and fix wall plates including straps and fixings to distribute roof loads to walls. | 21.6 | m | 17.38 | 375.31
Apex Roof (Storage Area)
125 | Supply and fix ridge boards or ridge beams to roof structure including joints and fixings. | 6 | m | 14.78 | 88.65
126 | Supply and fix collar ties or ties between rafters to provide stability. | 25.2 | m | 7.27 | 183.09
127 | Supply and fix ceiling joists including hangers and struts to support ceiling finishes. | 58.8 | m | 9.36 | 550.33
128 | Supply and fix roof rafters including birdsmouth cuts, fixings to wall plates and ridge. | 117 | m | 8.28 | 969.15
129 | Supply and fix wall plates including straps and fixings to distribute roof loads to walls. | 10.8 | m | 22.54 | 243.45
Flat Roof
130 | Supply and fix roof sheathing boards and firrings including fixings and jointing to form roof surface. | 26.7 | m2 | 40.53 | 1081.56
131 | Supply and install insulation within timber frame or stud walls to achieve thermal or acoustic performance. | 14.1 | m2 | 28.14 | 396.01
132 | Supply and fix uPVC gutters and downpipes including brackets, outlets and associated fittings. | 1 | each | 283.43 | 283.43
133 | Supply and install fibreglass roof coverings including matting, resin, trims and top coat to form waterproof flat roof. | 26.7 | m2 | 77.25 | 2061.66
134 | Supply and install lead or proprietary flashings to roof abutments, valleys and penetrations including fixings and sealant. | 1 | each | 1302.63 | 1302.63
135 | Supply and fix sheathing boards to timber frame walls including fixings. | 14.1 | m2 | 23.74 | 334.09
136 | Supply and install external cladding to timber frame walls including support battens, fixings and trims. | 14.1 | m2 | 79.08 | 1112.89
137 | Construct timber frame structure including studs, plates, bracing and connections ready for sheathing and cladding. | 1 | each | 1559.34 | 1559.34
138 | Supply and install insulation in roof spaces to achieve specified thermal performance. | 22.7 | m2 | 27.98 | 635.01
139 | Supply and install soffits and fascias including support battens, fixings, trims and ventilation slots. | 29.5 | m | 21.55 | 635.63
Slate Range
140 | Supply and fix roof battens to support tile or slate coverings including spacing and nailing. | 786.3 | m | 3.21 | 2521.11
141 | Supply and fix ridge tiles or ridge units including fixing clips, mortar bedding and pointing. | 16.8 | m | 52.58 | 883.35
142 | Provide eaves treatment including over-fascia vents, support trays and verge finishing details. | 33.6 | m | 7 | 235.1
143 | Supply and install verge tiles, ridge tiles, or verge trims with appropriate fixing and bedding. | 32.2 | m | 36.92 | 1188.89
144 | Supply and fix natural or artificial slate tiles including nails, laps and alignment. | 153.9 | m2 | 122.73 | 18888.46
145 | Supply and install breathable roof membrane over rafters and under battens including laps and temporary fixing. | 177 | m2 | 5.6 | 991.45
Pitched Roof Windows
146 | Supply and install roof windows including flashings, linings and internal finishes. | 3 | each | 930.63 | 2791.88
147 | Supply and fix rafters and trimmers around roof openings including trimming and fixings. | 1 | each | 567.65 | 567.65
Rafters Insulation
148 | Supply and install rigid or quilt insulation to floors, walls or roofs to achieve specified thermal performance. | 153.9 | m2 | 30.3 | 4663.64
Upvc
149 | Supply and fix raked soffit boards including support battens, fixings and joint trims. | 33 | m | 28.88 | 952.96
150 | Supply and fix soffit boards at eaves including support battens, fixings and ventilation slots. | 35 | m | 36.81 | 1288.31
151 | Supply and fix bargeboards to gable ends including fixings, joint trims and painting. | 33 | m | 25.59 | 844.56
152 | Supply and fix fascia boards including fixing to rafter ends, joint trims and painting. | 35 | m | 24.92 | 872.19
153 | Supply and form box end detail at junction of fascia and bargeboards including soffit panels and trims. | 7 | each | 58.09 | 406.61
Rainwater Goods
154 | Supply and fix uPVC downpipes including brackets, outlets and connection to drainage system. | 1 | each | 437.7 | 437.7
155 | Supply and fix uPVC gutters including brackets, outlets and connection to downpipes. | 1 | each | 533.36 | 533.36
Universal Column (Ridge Beam)
156 | Supply and install structural steel beams including fabrication, delivery, craneage, positioning and bolted connections. | 1 | each | 1937.65 | 1937.65
157 | Supply and install padstones or spreader blocks to support structural steel members. | 2 | each | 74.64 | 149.29
158 | Provide fire protection to structural steel members using intumescent coatings, board encasement or fire-rated linings. | 12.5 | m2 | 24.86 | 310.63
159 | Apply protective paint finish to structural steelwork including preparation and application of primer and top coats. | 12.5 | m2 | 6.95 | 86.84
Universal Column (Dormer Beam)
160 | Supply and install structural steel beams including fabrication, delivery, craneage, positioning and bolted connections. | 1 | each | 1937.65 | 1937.65
161 | Supply and install padstones or spreader blocks to support structural steel members. | 2 | each | 74.64 | 149.29
162 | Provide fire protection to structural steel members using intumescent coatings, board encasement or fire-rated linings. | 12.5 | m2 | 24.86 | 310.63
163 | Apply protective paint finish to structural steelwork including preparation and application of primer and top coats. | 12.5 | m2 | 6.95 | 86.84
Electrics
164 | Carry out first fix electrical installation including wiring, back boxes, conduits, cable trays and testing ready for second fix. | 1 | each | 5419.41 | 5419.41
165 | Carry out second fix electrical installation including switches, sockets, light fittings, circuit connections and testing. | 1 | each | 8473.49 | 8473.49
En Suite 1 Plumbing
166 | Carry out first fix plumbing installation including pipework runs, insulation, connections to appliances and testing. | 1 | each | 1077.16 | 1077.16
167 | Carry out second fix plumbing installation including fitting sanitary ware, taps, traps, pipework connections and testing. | 1 | each | 1393.91 | 1393.91
En Suite 2 Plumbing
168 | Carry out first fix plumbing installation including pipework runs, insulation, connections to appliances and testing. | 1 | each | 1077.16 | 1077.16
169 | Carry out second fix plumbing installation including fitting sanitary ware, taps, traps, pipework connections and testing. | 1 | each | 1393.91 | 1393.91
Bathroom Plumbing
170 | Carry out first fix plumbing installation including pipework runs, insulation, connections to appliances and testing. | 1 | each | 1131.1 | 1131.1
171 | Carry out second fix plumbing installation including fitting sanitary ware, taps, traps, pipework connections and testing. | 1 | each | 1282.25 | 1282.25
Kitchen Plumbing
172 | Carry out first fix plumbing installation including pipework runs, insulation, connections to appliances and testing. | 1 | each | 1000.01 | 1000.01
173 | Carry out second fix plumbing installation including fitting sanitary ware, taps, traps, pipework connections and testing. | 1 | each | 379.11 | 379.11
Heating
174 | Supply and install hot water cylinder including lagging, valves, pipe connections and testing. | 1 | each | 961.85 | 961.85
175 | Supply and install underfloor heating system including insulation, pipes, manifolds, controls and commissioning. | 1 | each | 3420.36 | 3420.36
176 | Carry out first fix mechanical and electrical installations including pipework, wiring and fittings ready for second fix. | 1 | each | 1875 | 1875
177 | Provide below-ground drainage connections for services including pipes, gullies, traps, backfilling and testing. | 1 | each | 625 | 625
178 | Allow for mechanical and electrical services provision including associated fittings, testing and commissioning. | 1 | each | 9375.1 | 9375.1
Plasterboard on battens
179 | Fix plasterboard linings to walls or ceilings including framing, screws, joint tape and beads. | 153.9 | m2 | 40.51 | 6234.2
180 | Supply and fix battens to support plasterboard linings or finishes including fixings and spacings. | 451.3 | m | 6.48 | 2926.14
181 | Apply skim coat plaster to ceilings to achieve smooth finish ready for decoration. | 153.9 | m2 | 13.16 | 2025.64
182 | Supply and fix accessories such as angle beads, stop beads and jointing materials for plasterboard and plaster finishes. | 50 | each | 8.09 | 404.38
Plasterboard on battens (GF Ceiling)
183 | Fix plasterboard linings to walls or ceilings including framing, screws, joint tape and beads. | 74.3 | m2 | 19.59 | 1455.42
184 | Supply and fix battens to support plasterboard linings or finishes including fixings and spacings. | 219.1 | m | 6.48 | 1419.91
185 | Apply skim coat plaster to ceilings to achieve smooth finish ready for decoration. | 74.3 | m2 | 13.25 | 984.79
186 | Supply and fix accessories such as angle beads, stop beads and jointing materials for plasterboard and plaster finishes. | 20 | each | 8.09 | 161.75
Decorating
187 | Prepare and paint ceilings including filling, sanding, priming and applying two coats of emulsion paint. | 228.2 | m2 | 10.94 | 2497.44
188 | Prepare and paint walls including filling, sanding, priming and applying two coats of emulsion paint. | 272.5 | m2 | 9.6 | 2615.31
Timber Cladding
189 | Supply and install membrane behind cladding to provide waterproof barrier including laps and fixing to substrate. | 65 | m2 | 5.34 | 347.42
190 | Supply and fix support battens for cladding including fixings and spacings to receive external cladding. | 166 | m | 6.01 | 998.46
191 | Supply and install cladding boards or panels to external walls including support battens, fixings, trims and finishing. | 65 | m2 | 88.39 | 5745.25
192 | Prepare and apply finishing coats to cladding boards including priming, undercoating and painting. | 65 | m2 | 25.5 | 1657.4
Kitchen
193 | Supply and install kitchen units including base and wall cabinets, worktops, drawers, sink, taps and associated fittings. | 1 | each | 10925 | 10925
Single Door (FF)
194 | Supply and fix skirting board or architrave to door/window openings including mitres, fixings and priming ready for decoration. | 21.6 | m | 28 | 604.8
195 | Supply and install precast concrete or steel lintels over openings including bearings and installation. | 4 | each | 27 | 108.01
196 | Supply and install internal door including lining, stops, architraves, hinges, handles and latches. | 2 | each | 394.18 | 788.36
Double Door (FF)
197 | Supply and fix skirting board or architrave to door/window openings including mitres, fixings and priming ready for decoration. | 12.2 | m | 31.48 | 384.1
198 | Supply and install precast concrete or steel lintels over openings including bearings and installation. | 2 | each | 54.01 | 108.01
199 | Supply and install internal door including lining, stops, architraves, hinges, handles and latches. | 1 | each | 762.23 | 762.23
Single Pocket Door (FF)
200 | Supply and fix skirting board or architrave to door/window openings including mitres, fixings and priming ready for decoration. | 21.6 | m | 28 | 604.8
201 | Supply and install precast concrete or steel lintels over openings including bearings and installation. | 4 | each | 27 | 108.01
202 | Supply and install internal door including lining, stops, architraves, hinges, handles and latches. | 2 | each | 716.92 | 1433.85
Double Sliding Door (FF)
203 | Supply and fix skirting board or architrave to door/window openings including mitres, fixings and priming ready for decoration. | 24.4 | m | 27.55 | 672.11
204 | Supply and install precast concrete or steel lintels over openings including bearings and installation. | 4 | each | 54.01 | 216.03
205 | Supply and install internal door including lining, stops, architraves, hinges, handles and latches. | 2 | each | 867.28 | 1734.56
Single Door (FF)
206 | Supply and fix skirting board or architrave to door/window openings including mitres, fixings and priming ready for decoration. | 21.6 | m | 28 | 604.8
207 | Supply and install precast concrete or steel lintels over openings including bearings and installation. | 4 | each | 27 | 108.01
208 | Supply and install internal door including lining, stops, architraves, hinges, handles and latches. | 2 | each | 394.18 | 788.36
Double Door (GF)
209 | Supply and fix skirting board or architrave to door/window openings including mitres, fixings and priming ready for decoration. | 12.2 | m | 31.48 | 384.1
210 | Supply and install precast concrete or steel lintels over openings including bearings and installation. | 2 | each | 50.51 | 101.03
211 | Supply and install internal door including lining, stops, architraves, hinges, handles and latches. | 1 | each | 762.23 | 762.23
Double Folding Door (GF)
212 | Supply and fix skirting board or architrave to door/window openings including mitres, fixings and priming ready for decoration. | 12.2 | m | 31.48 | 384.1
213 | Supply and install precast concrete or steel lintels over openings including bearings and installation. | 2 | each | 50.51 | 101.03
214 | Supply and install internal door including lining, stops, architraves, hinges, handles and latches. | 1 | each | 1000.91 | 1000.91
Staircase
215 | Supply and install staircase including strings, treads, risers, balustrades and handrails. | 1 | each | 1778.96 | 1778.96
216 | Prepare and paint woodwork including filling, sanding, priming, undercoating and applying top coats. | 8 | m | 17.24 | 137.91
Balustrade
217 | Prepare and paint woodwork including filling, sanding, priming, undercoating and applying top coats. | 46.6 | m | 9.69 | 451.54
218 | Supply and install balustrade including posts, handrails, balusters, fixings and finishing. | 1 | each | 1195.43 | 1195.43
Skirting Board
219 | Decorate surfaces including filling, sanding, priming and applying paints, stains or finishes as specified. | 155 | m | 11.98 | 1856.25
220 | Supply and fix skirting boards including mitred corners, fixing to walls and priming ready for painting. | 155 | m | 13.08 | 2027.91
Window Board
221 | Supply and fix window boards including fixing, jointing and finishing. | 14.4 | m | 26.41 | 380.29
222 | Prepare and decorate window boards including sanding, priming and applying paint finish. | 3.9 | m2 | 46.53 | 180.09
Boxing
223 | Supply and fix timber framing for structural or finish purposes including cutting, jointing and fixing. | 38.4 | m | 12.11 | 465.21
224 | Supply and install plywood box linings to openings or recesses including fixings and finishing. | 8.6 | m2 | 24.25 | 209.49
Resin
225 | Load and cart away surplus excavated soil from site to a licensed tip as required. | 33.5 | m3 | 68.24 | 2289.45
226 | Supply and lay geotextile membrane to sub-base of paving or landscaping works. | 110 | m2 | 3.74 | 411.45
227 | Construct in-situ concrete slab including reinforcement, placing, compaction, finishing and curing. | 11 | m3 | 408.76 | 4496.31
228 | Excavate to reduce ground levels to formation including disposal of surplus material and trimming to level. | 27.5 | m3 | 80.37 | 2210.15
229 | Supply and compact sub-base material to required thickness for paving or driveways. | 16.5 | m3 | 261.01 | 4306.7
230 | Supply and lay resin bound or bonded surfacing including base preparation, edging and curing. | 110 | m2 | 47.93 | 5272.44
Fence
231 | Supply and fix gravel boards at base of fencing panels to prevent rot and retain soil. | 43 | each | 35.39 | 1521.75
232 | Supply and install gates including frames, posts, hinges, latches and finishes to match fencing. | 2 | each | 457.5 | 915
233 | Supply and place in-situ concrete to foundations or slabs including mixing, transport, laying, compacting and curing. | 2 | m3 | 373.33 | 739.2
234 | Decorate surfaces including filling, sanding, priming and applying paints, stains or finishes as specified. | 240.1 | m2 | 8.39 | 2015.22
235 | Supply and erect timber fencing panels including posts, fixings, treatment and painting. | 43 | each | 79.7 | 3427.1
236 | Excavate for foundations, footings or slabs to required levels including removal of spoil, support of sides and keeping excavations free of water. | 4.2 | m3 | 243.63 | 1029.08
237 | Load and cart away surplus excavated soil from site to a licensed tip as required. | 5.2 | m3 | 85.4 | 440.1
238 | Supply and install fence posts including holes, concrete foundations and fixings. | 44 | each | 58.5 | 2574.05
Turf
239 | Excavate to reduce ground levels to formation including disposal of surplus material and trimming to level. | 5 | m3 | 185.17 | 925.84
240 | Supply and lay cultivated turf or grass seed to prepared soil including watering and maintenance until established. | 50 | m2 | 10.77 | 538.58
241 | Cultivate and prepare soil for seeding or planting including fertiliser application and stone removal. | 50 | m2 | 6.73 | 336.61
242 | Supply and spread top soil to specified depth including levelling and raking. | 5 | m3 | 77.57 | 387.86
243 | Load and cart away surplus excavated soil from site to a licensed tip as required. | 6.1 | m3 | 73.55 | 448.65
Sub Total |  |  |  |  | 373509.24

## Labour
Labour
Description | Quantity | Unit | Rate | Total
All
Laying vapour control | 93.8 | m2 | 1.8 | 168.88
Carpentry
Fix solid strutting between joist | 23.5 | m | 14.5 | 340.46
Fix Restraint Strap | 2 | each | 14.5 | 29
Laying wool insulation between timbers | 74.3 | m2 | 7.5 | 557.55
Fixing T&G chipboard flooring | 74.3 | m2 | 16.48 | 1224.93
Carpenter to fit floor joists | 226.8 | m | 7.97 | 1808.72
Carpenter to fit roof collar | 103.2 | m | 4.71 | 486.32
Install rafters | 514.2 | m | 4.71 | 2423.16
Fixing plywood | 127.2 | m2 | 15.23 | 1936.64
Fixing firrings to joists | 82 | m | 1.45 | 118.9
Laying PIR insulation between studs | 14.1 | m2 | 13.64 | 191.86
Fixing battens to timber | 854 | m | 2.01 | 1719.8
Fixing breather membrane | 14.1 | m2 | 2.73 | 38.38
Erect and fix studwork | 77 | m | 8.63 | 664.59
Install rafters | 82 | m | 4.53 | 371.56
Install window header | 4 | m | 8.63 | 34.52
Laying PIR insulation between rafters | 22.7 | m2 | 13.64 | 309.41
Install fascia / soffit | 7.8 | hour | 36.25 | 282.02
Erect and fix studwork | 297.6 | m | 8.63 | 2568.58
Laying wool insulation between studs | 77.8 | m2 | 7.5 | 583.13
Install ridge | 6 | m | 8.7 | 52.2
Carpenter to fit ceiling joists | 58.8 | m | 4.71 | 277.1
Laying PIR insulation between rafters | 153.9 | m2 | 13.64 | 2098.64
Carpenter to fit joist hangers | 18 | each | 9.06 | 163.13
Fixing battens to masonry | 942.8 | m | 4.53 | 4272.01
Fixing breather membrane | 242 | m2 | 2.73 | 659.98
Cutting and fixing in position architraves | 125.8 | m | 5.44 | 684.04
Install timber lintel | 12 | each | 15.66 | 187.93
Fitting a single door lining | 6 | each | 29 | 174
Fitting a tubular latch | 11 | each | 30.81 | 338.94
Fitting handles | 16 | each | 10.88 | 174
Fitting a door | 8 | each | 60.42 | 483.34
Install timber lintel | 6 | each | 31.32 | 187.93
Fitting a double door lining | 5 | each | 39.88 | 199.38
Fitting internal pocket door | 2 | each | 163.13 | 326.25
Fitting internal sliding door | 4 | each | 101.5 | 406
Fitting internal folding door | 2 | each | 112.38 | 224.75
Install window board | 14.4 | m | 14.5 | 208.8
Cutting and fixing skirting board | 155 | m | 7.25 | 1123.75
Install prefabricated staircase | 1 | each | 652.5 | 652.5
Install stair parts | 1 | each | 677.88 | 677.88
Install kitchen | 1 | each | 2175 | 2175
Decoration
Apply 2 coats of oil, 7.7m2 x 2 | 15.4 | m2 | 9.5 | 146.3
Applying intumescent paint | 46.2 | m2 | 10 | 461.8
Apply 1 coat of primer, 21.2m2 x 1 | 21.2 | m2 | 5 | 105.9
Apply 1 coat of primer, 12.5m2 x 1 | 25 | m2 | 5 | 125
Apply 2 coats of gloss, 21.6m x 2 | 129.6 | m | 3.13 | 405
Apply 1 coat of primer, 21.6m x 1 | 64.8 | m | 2.5 | 162
Apply 1 coat of undercoat, 21.6m x 1 | 64.8 | m | 2.5 | 162
Apply 2 coats of gloss, 8m2 x 2 | 48 | m2 | 11 | 528
Apply 1 coat of primer, 8m2 x 1 | 24 | m2 | 5 | 120
Apply 1 coat of undercoat, 8m2 x 1 | 24 | m2 | 5 | 120
Apply 2 coats of gloss, 12.2m x 2 | 73.2 | m | 3.13 | 228.75
Apply 1 coat of primer, 12.2m x 1 | 36.6 | m | 2.5 | 91.5
Apply 1 coat of undercoat, 12.2m x 1 | 36.6 | m | 2.5 | 91.5
Apply 2 coats of gloss, 7.4m2 x 2 | 29.6 | m2 | 11 | 325.6
Apply 1 coat of primer, 7.4m2 x 1 | 14.8 | m2 | 5 | 74
Apply 1 coat of undercoat, 7.4m2 x 1 | 14.8 | m2 | 5 | 74
Apply 2 coats of gloss, 24.4m x 2 | 48.8 | m | 3.13 | 152.5
Apply 1 coat of primer, 24.4m x 1 | 24.4 | m | 2.5 | 61
Apply 1 coat of undercoat, 24.4m x 1 | 24.4 | m | 2.5 | 61
Apply 2 coats of gloss, 14.8m2 x 2 | 29.6 | m2 | 11 | 325.6
Apply 1 coat of primer, 14.8m2 x 1 | 14.8 | m2 | 5 | 74
Apply 1 coat of undercoat, 14.8m2 x 1 | 14.8 | m2 | 5 | 74
Apply 2 coats of gloss, 7.3m2 x 2 | 14.6 | m2 | 11 | 160.6
Apply 1 coat of primer, 7.3m2 x 1 | 7.3 | m2 | 5 | 36.5
Apply 1 coat of undercoat, 7.3m2 x 1 | 7.3 | m2 | 5 | 36.5
Apply 2 coats of gloss, 3.9m² x 2 | 7.7 | m2 | 11 | 85.14
Apply 1 coat of primer, 3.9m² x 1 | 3.9 | m2 | 5 | 19.35
Apply 1 coat of undercoat, 3.9m² x 1 | 3.9 | m2 | 5 | 19.35
Apply 2 coats of gloss, 155m x 2 | 310 | m | 3.13 | 968.75
Apply 1 coat of primer, 155m x 1 | 155 | m | 2.5 | 387.5
Apply 1 coat of undercoat, 155m x 1 | 155 | m | 2.5 | 387.5
Apply 1 coat of gloss 8m x 1 | 8 | m | 3.13 | 25
Apply 1 coat of primer 8m x 1 | 8 | m | 2.5 | 20
Apply 1 coat of undercoat 8m x 1 | 8 | m | 2.5 | 20
Apply 1 coat of gloss 46.6m x 1 | 46.6 | m | 3.13 | 145.63
Apply 1 coat of primer 46.6m x 1 | 46.6 | m | 2.5 | 116.5
Apply 1 coat of undercoat 46.6m x 1 | 46.6 | m | 2.5 | 116.5
Painting ceiling - mist coat and 2 full coats, 3 x 228.2m2 | 684.6 | m2 | 3.03 | 2074.55
Painting walls - mist coat and 2 full coats, 3 x 272.5m2 | 817.5 | m2 | 2.58 | 2106.96
Apply 2 coats of oil, 65m2 x 2 | 130 | m2 | 9.5 | 1235
Drainage
Install chambers, covers and fittings | 7.4 | hour | 30 | 222
Install drainage pipes and fittings | 13.4 | hour | 30 | 402
Install aco channels | 6 | each | 10 | 60
Install soakaway crates | 7.3 | each | 3.75 | 27.45
Install rainwater goods and accessories | 27.8 | hour | 30 | 834
Electrics
Electrics 1st Fix | 110.2 | hour | 40 | 4406
General Electrics | 114.7 | hour | 40 | 4586
New Installation certificate | 1 | each | 200 | 200
Demolition
Remove block paving | 15 | m2 | 13.5 | 202.5
Removal top soil | 21.5 | m3 | 195 | 4192.5
Remove large tree | 1 | each | 750 | 750
Finishes
Fixing cladding | 79.1 | m2 | 37.5 | 2965.13
Landscaping
Laying geotextile membrane | 121.7 | m2 | 1.2 | 145.99
Laying resin bonded | 110 | m2 | 33 | 3630
Laying turf | 50 | m2 | 6.9 | 344.83
Cultivate 150mm deep, remove stones | 50 | m2 | 5.36 | 267.86
Setting gravel board | 43 | each | 10.49 | 451.05
Install gate | 2 | each | 145 | 290
Backfill hole with concrete | 2 | m3 | 40 | 79.2
Painting fence | 240.1 | m2 | 6 | 1440.42
Setting fence panel | 43 | each | 7.5 | 322.5
Excavating holes (auger) | 4.2 | m3 | 135 | 569.7
Setting concrete post | 44 | each | 14.4 | 633.6
Openings
Fit window | 1 | each | 124.5 | 124.5
Install cavity closers | 55.6 | m | 5.66 | 314.71
Install trickle vents | 11 | each | 7.5 | 82.5
Fit window | 3 | each | 99 | 297
Fit window | 1 | each | 106.5 | 106.5
Fit window | 2 | each | 105 | 210
Fit window | 2 | each | 96 | 192
Fit window | 1 | each | 103.5 | 103.5
Fit window | 1 | each | 100.5 | 100.5
Install bifold door | 1 | each | 200 | 200
Plastering
Dot and dabbing plasterboard | 323 | m2 | 7.5 | 2422.5
Skimming walls | 478.5 | m2 | 9.09 | 4350
Fixing plasterboard to walls | 155.5 | m2 | 8.33 | 1295.84
Fixing plasterboard to ceiling | 228.2 | m2 | 14.29 | 3260
Skimming ceiling | 228.2 | m2 | 11.54 | 2633.07
Fixing plaster beads and accessories | 14 | hour | 30 | 420
Plumbing
1st Fix Plumbing | 30.1 | hour | 37.5 | 1126.88
2nd Fix Plumbing | 41.4 | hour | 37.5 | 1551
Install hot water cylinder | 6.4 | hour | 37.5 | 240
Install wet underfloor heating | 53.6 | hour | 37.5 | 2010
Roof
Install GRP roof | 26.7 | m2 | 44.96 | 1200.06
Install flashings | 18 | hour | 37.5 | 675
Install roof window | 3 | each | 249.38 | 748.13
Install fascia/soffit 150-300mm | 136 | m | 13.82 | 1880.19
Install box end | 7 | each | 33.33 | 233.34
Bedding ridge/hips tiles | 16.8 | m | 34.09 | 572.73
Fix eaves support | 33.6 | m | 4.69 | 157.5
Pointing verges, inc fixing clips | 32.2 | m | 19.74 | 635.52
Fix undercloack | 32.2 | m | 5.36 | 172.5
Fix slates | 154.1 | m2 | 34.09 | 5253.06
Preparation
General Labourer | 120 | hour | 20 | 2400
Site Supervision | 160 | hour | 43.75 | 7000
Install temporary fence | 105.3 | m | 3.61 | 380.6
Excavating and Filling
Fill to excavations by hand | 8.7 | m3 | 27.27 | 235.91
Load soil to skip by machine | 133.9 | m3 | 9 | 1204.83
Levelling and compacting bottoms of excavations | 296.1 | m2 | 2.73 | 807.69
Excavate Pit by Hand | 0.8 | m3 | 150 | 127.5
Excavate trenches by Hand | 11.3 | m3 | 111.11 | 1252.22
Fill to make up levels by hand | 39.1 | m3 | 57.6 | 2251.01
Excavate trenches by Machine | 32.6 | m3 | 48.39 | 1575.96
Spreading and levelling fill | 331 | m2 | 1.08 | 357.48
Compacting fill | 281 | m2 | 1.36 | 383.19
Excavate reduced levels by Machine | 61.3 | m3 | 48.39 | 2964.67
Laying Damp Proof Membrane | 96.6 | m2 | 1.5 | 144.9
Excavate reduced levels by Hand | 5 | m3 | 157.89 | 789.48
Concrete Works
Casting concrete to trench | 13.6 | m3 | 57 | 778.05
Mix Concrete on Site | 12.9 | m3 | 50 | 647
Casting concrete to slabs | 23.8 | m3 | 66 | 1572.78
Tamped finish | 85.5 | m2 | 4.5 | 384.75
Precast Concrete
Install Padstone | 8 | each | 40 | 320
Install concrete lintel | 4 | each | 31 | 124
Masonry
Filling cavity | 1.6 | m3 | 81.08 | 133.79
Laying concrete blocks | 3170.9 | each | 2.71 | 8600.99
Lay damp proof course | 98 | m | 3.88 | 379.75
Laying bricks (half a brick thick) | 218.3 | m2 | 42.63 | 9302.91
Forming cavity | 206 | m2 | 1.49 | 307.02
Laying PIR insulation to cavity wall | 206 | m2 | 4.65 | 957.9
Install steel lintel | 4 | each | 13.95 | 55.8
Install steel lintel | 4 | each | 11.63 | 46.5
Install steel lintel | 5 | each | 7.75 | 38.75
Install steel lintel | 1 | each | 9.3 | 9.3
Install steel lintel | 1 | each | 77.5 | 77.5
Install front door | 3 | each | 115.38 | 346.15
Bedding wall plate | 32.4 | m | 6.6 | 213.84
Flooring
Laying floor screed 65-100mm | 85.5 | m2 | 10 | 855
Laying insulation to floor | 93.8 | m2 | 6 | 562.92
Fix chicken wire | 152.8 | m2 | 3.75 | 572.85
Structural
Erecting and setting in position metal beam | 125.2 | hour | 30 | 3756
Drilling steel | 40 | each | 6 | 240
Fixing bolts | 16 | each | 2.5 | 40
Other
Labourer | 124.1 | hour | 30 | 3722.1
Subtotal |  |  |  | 159049.09

## Materials
Material
Description | Quantity | Unit | Rate | Total
Aggregates
10mm Gravel/Shingle Bulk Bag | 9 | each | 81.25 | 731.25
Ballast Bulk Bag | 28 | each | 81.25 | 2275
Blue Circle Mastercrete 25kg | 332 | each | 7.81 | 2593.75
Building Sand Bulk Bag | 26 | each | 81.25 | 2112.5
Blue Circle Cement 25kg | 151 | each | 7.03 | 1060.78
Sharp Sand Bulk Bag | 15 | each | 81.25 | 1218.75
MOT Type 1 Sub-base Bulk Bag | 67 | bag | 81.25 | 5443.75
Building Sand 25kg Bag | 3 | each | 3.85 | 11.55
1-3 mm Resin Aggregate 25kg bag | 75 | bag | 8.74 | 655.31
Top Soil (20 ton min) | 8 | t | 24.69 | 197.5
Lintels
Cavity Wall Lintel CG150/100 1800mm | 4 | each | 138.51 | 554.05
Cavity Wall Lintel CG150/100 1500mm | 4 | each | 115.43 | 461.7
Cavity Wall Lintel CG150/100 1050mm | 1 | each | 80.81 | 80.81
Cavity Wall Lintel CG150/100 900mm | 4 | each | 69.26 | 277.05
Cavity Wall Lintel CG150/100 1200mm | 1 | each | 92.34 | 92.34
Catnic Open Back Cavity Wall Extra Heavy Duty Lintel 4575mm CX90/100 | 1 | each | 1128.84 | 1128.84
Doors and Joinery
1 x White uPVC Window 1475(W) x 2050(H), Clear glass | 1 | each | 459.64 | 459.64
UPVC Trickle Vent | 11 | each | 11.13 | 122.38
1 x White uPVC Window 910(W) x 900(H), Clear glass | 1 | each | 222.91 | 222.91
1 x White uPVC Window 685(W) x 1200(H), Clear glass | 1 | each | 225.09 | 225.09
1 x White uPVC Window 1250(W) x 1200(H), Clear glass | 1 | each | 298.85 | 298.85
2 x White uPVC Window 1500(W) x 900(H), Obscure glass | 2 | each | 395.42 | 790.85
2 x White uPVC Window 600(W) x 900(H), Obscure glass | 2 | each | 285.96 | 571.93
1 x White uPVC Window 575(W) x 2100(H), Obscure glass | 1 | each | 320.09 | 320.09
1 x White uPVC Window 900(W) x 1050(H), Obscure glass | 1 | each | 277.7 | 277.7
1 x White uPVC Window 400(W) x 2100(H), Obscure glass | 1 | each | 274.15 | 274.15
White uPVC Bifold Door 4.2m | 1 | each | 4410.24 | 4410.24
Composite Front Door 920 x 2085mm | 1 | each | 885.41 | 885.41
Cottage Panelled White Oak Veneer Front Door & Frame with Letter Plate, (H)2125mm (W)907mm | 2 | each | 517.71 | 1035.42
Wickes Geneva White Grained Moulded Cottage Internal Door - 1981 x 762mm | 8 | each | 48.75 | 390
Softwood Door Lining Set + Stops 32 x 115mm | 6 | each | 20.76 | 124.57
Eclipse Fire Door Ball Bearing Hinges 102 x 76mm Pack of 3 | 8 | pack | 9.34 | 74.7
Tubular Latch 76 mm | 11 | each | 3.63 | 39.88
Brass Door Handle Pack of 2 | 16 | pack | 9.89 | 158.2
Softwood Double Door Lining Set + Stops 32 x 115mm | 5 | each | 87.15 | 435.75
6 Panel Hollow Door 762 x1981mm | 6 | each | 48.96 | 293.78
Henderson Pocket 1 Door Sliding Track System 1601mm | 2 | each | 229.16 | 458.33
Henderson 1 Door Sliding Track System 1449mm | 4 | each | 32.81 | 131.25
Bi-Fold 2 Door Folding Track System 1067mm | 2 | each | 36.45 | 72.9
4 panel Unglazed White Internal Bi-fold Door set,750 x 1950mm | 2 | each | 90.63 | 181.25
Double Winder Staircase, MDF treads and risers | 1 | each | 1045.21 | 1045.21
Pine 41mm Traditional Turned Spindle 900mm | 32 | each | 4.65 | 148.8
Pine 41mm HDR Profile Heavy Hand Rail 3600mm | 2 | each | 70.84 | 141.68
Pine 90mm Plain Square Full Newel Post 1500mm | 2 | each | 43.75 | 87.5
Pine 41mm Base Rail 3600mm | 2 | each | 57.81 | 115.63
Pine Full Pyramid Cap for 90mm Newel Posts | 2 | each | 11.97 | 23.95
Roofing
Cure-It GRP Resin 20kg | 2 | each | 128.91 | 257.82
Cure-It GRP 450g Chopped Strand Matting 15m x 0.95m | 2 | each | 36.09 | 72.17
Cure-It GRP Coloured Topcoat Anthracite Grey 20kg | 1 | each | 216.41 | 216.41
Cure-It GRP Summer Catalyst 1L | 2 | each | 17.49 | 34.98
Cure-It GRP 75mm Glass Bandage 65m | 1 | each | 30.64 | 30.64
Cure-It Acetone 5L | 3 | each | 19.3 | 57.9
Cure-It GRP - 3 Inch Resin Brush | 3 | each | 1.72 | 5.17
Cure-It GRP - Soft Application 6 Inch Roller Set | 1 | each | 2.92 | 2.92
Cure-It GRP Paddle Roller 6" (150mm) | 2 | each | 8.16 | 16.32
Cure-It GRP Plain Mixing Bucket 10L | 4 | each | 2.54 | 10.15
Cure-It GRP B230 Raised edge Trim 3m | 3 | each | 16.85 | 50.55
Cure-It GRP A200 Fascia/Drip Trim 3m | 3 | each | 16.24 | 48.71
Cure-It GRP Trim PU Adhesive | 2 | each | 8.9 | 17.8
Code 4 Lead Roll 300mm x 6m | 5 | roll | 125.53 | 627.63
Cromar Vent 3 High Performance 1 x 50m Breathable Felt | 3 | each | 85.08 | 255.23
Velux GGL MK04 Pine Roof WIndow 780 x 980mm | 3 | each | 501.25 | 1503.75
Velux EDW MK04 Tile Flashing 780 x 980mm | 3 | each | 141.25 | 423.75
Velux BFX MK04 Underfelt Collar 780 x 980mm | 3 | each | 38.75 | 116.25
Marley Segmental Ridge Tile Natural Red (Fine Sanded) | 37 | each | 5.25 | 194.25
Plastic Eaves Support tray 1.5m | 25 | each | 2.69 | 67.19
Verges clips | 161 | each | 1.07 | 173.08
Undercloak 150 x 1200 mm | 27 | each | 3 | 81
Copper nails 30mm x 1kg | 16 | pack | 25 | 400
SSQ Del Prado Natural Slate 500 x 250mm | 3078 | each | 4.3 | 13235.4
Tyvek Supro Breather Membrane 1 x 50m | 4 | each | 127.19 | 508.75
Landscaping
4TRADE Heavy Duty Landscape Fabric 1m x 20m | 7 | roll | 46.57 | 326.02
Bonded Resin - 2 part Kit 17.5 | 10 | kit | 98.71 | 987.13
Bulk Turf | 50 | m2 | 3.88 | 193.75
Supreme Concrete Recessed Gravel Board 50 x 150 x 1830mm | 43 | each | 24.9 | 1070.7
Gate allowance | 2 | each | 312.5 | 625
Blue Circle Ready to Use Postcrete 20kg | 88 | each | 7.5 | 660
Close Board Dip Treated Fence Panel 1830 x 1520mm (5FT) | 43 | each | 72.2 | 3104.6
Supreme Concrete Slotted Fence Post 2440mm (8FT) | 41 | each | 39.02 | 1600.03
Supreme Concrete Corner Slotted Fence Post 125 x 125 x 2440mm | 3 | each | 113.47 | 340.42
Electrics
2.5mm² Twin and Earth Cable 100m Reel | 4 | reel | 78.11 | 312.45
1.5mm² Twin and Earth Cable 100m Reel | 4 | reel | 55.2 | 220.8
Metal Box 2 Gang 35mm | 43 | each | 0.84 | 36.01
Metal Box 1 Gang 35mm | 37 | each | 0.72 | 26.83
10mm² Twin and Earth Cable 50m Reel | 2 | reel | 171.86 | 343.73
1.0mm² 3-Core and Earth Cable 100m Reel | 1 | reel | 67.6 | 67.6
Metal Box 1 Gang 47mm | 5 | each | 1.2 | 6
MK DP Switched Socket 13A 2 Gang White | 40 | each | 4.68 | 187
MK Light Switch 1 Gang 2 Way White | 18 | each | 2.6 | 46.8
100mm Low Profile Extractor Fan Humidistat | 2 | each | 35.41 | 70.82
Triton Enrich Manual Electric Shower White 8.5kW | 3 | each | 71.86 | 215.59
MK 13A DP Spur Unit Switched Neon White | 6 | each | 11.24 | 67.42
Mains Smoke Detector With 9V Battery Backup | 2 | each | 19.79 | 39.58
MK Cooker Switch & Socket 45A 1 Gang with Neon White | 2 | each | 33.85 | 67.7
MK Pull Cord Switch 50A with Neon White | 3 | each | 18.74 | 56.21
Fan Isolator Switch 3 Pole | 2 | each | 18.59 | 37.17
Fire Rated Fixed IP65 GU10 Downlight White | 50 | each | 12.65 | 632.5
Mains Heat Alarm With 9V Battery Backup | 1 | each | 22.91 | 22.91
TV Point Single White | 4 | each | 1.04 | 4.15
BT Telephone Point Slave White | 2 | each | 2.17 | 4.35
RJ45 Cat5E Wall Outlet Double | 4 | each | 5.2 | 20.8
Outdoor Light allowance | 7 | each | 31.25 | 218.75
IP66 Masterseal Plus Socket 2 Gang | 1 | each | 43.74 | 43.74
Consumer Unit Allowance | 1 | each | 375 | 375
Dual Voltage Shaver Socket White | 3 | each | 25.66 | 76.99
Heater Allowance | 3 | each | 375 | 1125
Electric Towel Radiator allowance | 2 | each | 187.5 | 375
Plumbing
Full Bore Isolating Valve 15 mm | 15 | each | 3.7 | 55.5
Flexible Hose 15mm x 1/2 x 300mm | 11 | each | 2.07 | 22.83
Copper Pipe Ø15 mm, 3 m Length | 37 | each | 10.94 | 404.69
Fittings allowance | 4 | each | 37.5 | 150
Drainage Pipes and Fittings | 5 | each | 625 | 3125
Toilet allowance | 3 | each | 187.5 | 562.5
Basin allowance | 2 | each | 150 | 300
Basin Taps allowance | 3 | each | 93.75 | 281.25
90° Pan Connector | 3 | each | 7.69 | 23.06
Trap and Waste Kit 32mm | 3 | each | 23.06 | 69.19
Shower Tray allowance | 2 | each | 187.5 | 375
Shower Enclosure allowance | 2 | each | 250 | 500
Shower Trap 70 mm Chrome | 2 | each | 24.16 | 48.32
Full Bore Isolating Valve 22 mm | 2 | each | 8.31 | 16.63
Flexible Hose 22mm x 3/4 x 300mm | 2 | each | 3.13 | 6.25
Copper Pipe Ø22 mm, 3 m Length | 4 | each | 22.91 | 91.65
Bath allowance | 1 | each | 312.5 | 312.5
Mixer Tap allowance | 1 | each | 125 | 125
McAlpine Bath trap with waste Top Access 1 1/2" | 1 | each | 29.63 | 29.63
Basin allowance | 1 | each | 156.25 | 156.25
Washing Machine Valve With CV 15mm x 3/4 | 2 | each | 4.26 | 8.53
Kitchen Sink allowance | 1 | each | 62.5 | 62.5
Kitchen Tap supplied by client | 1 | each | 0 | 0
Double Bowl Sink Trap Kit 40 mm | 1 | each | 25.94 | 25.94
Washing Machine supplied by client | 1 | each | 0 | 0
Appliance Trap 40 mm | 2 | each | 13.53 | 27.05
Dishwasher supplied by client | 1 | each | 0 | 0
Pipes and Fittings allowance | 1 | each | 1875 | 1875
Materials | 1 | each | 6250 | 6250
Flooring
Concrete and screed Fibres 900g (usage 1m3 screed) | 7 | each | 22.7 | 158.9
Chicken Wire/ Mesh Roll 1m x 10m (10m2) | 16 | each | 23.42 | 374.8
Chipboard Flooring P4 2400 x 600 x 18mm | 52 | each | 13.51 | 702.65
Concrete
Concrete Mix C25 | 14 | m3 | 146.25 | 2047.5
Concrete Mix C35 | 13 | m3 | 156.25 | 2031.25
Concrete Part Load Charge | 2 | m3 | 68.75 | 137.5
Timber
Sawn Timber Treated C16/C24 47 x 95mm | 21 | m | 2.26 | 47.51
Posi Joist 72 x 202mm x 5.4m | 227 | m | 11.15 | 2531.05
Sawn Timber Treated C16/C24 47 x 95mm x 3m | 78 | m | 2.26 | 176.48
Sawn Timber Treated C16/C24 47 x 145mm x 6m | 354 | m | 3.4 | 1203.6
Sawn Timber Treated C16/C24 47 x 95mm x 5.4m | 33 | m | 2.26 | 74.66
Smartply OSB 2440 x 1220 x 18mm | 10 | sheet | 23.96 | 239.63
Softwood treated firring | 82 | m | 3.5 | 287
Treated Batten 25 x 50mm | 724 | m | 1.46 | 1058.85
Smartply OSB 2440 x 1220 x 9mm | 5 | sheet | 20.84 | 104.19
Treated Batten 25 x 38mm | 1021 | m | 1.14 | 1161.39
Studs - Sawn Timber Treated C16/C24 47 x 95mm | 77 | m | 2.26 | 174.21
Rafters - Sawn Timber Treated C16/C24 47 x 145mm | 82 | m | 3.4 | 278.8
Header - Sawn Timber Treated C16/C24 47 x 145mm | 4 | m | 3.4 | 13.6
Sawn Timber Treated C16/C24 47 x 95mm&lt;br&gt;Studs: 82 x 2.4m. Plates: 14 x 4.8m. Noggins: 7 x 4.8m | 298 | m | 2.26 | 674.23
Smartply OSB 2440 x 1220 x 12mm | 27 | sheet | 26.04 | 703.01
Sawn Timber Treated C16/C24 47 x 225mm x 6m | 6 | m | 6.08 | 36.45
Sawn Timber Treated C16/C24 47 x 95mm x 3.6m | 26 | m | 2.26 | 58.83
Sawn Timber Treated C16/C24 47 x 195mm x 4.2m | 59 | m | 4.54 | 267.71
Sawn Timber Treated C16/C24 47 x 145mm x 3m | 117 | m | 3.4 | 397.8
47 x 145 mm (2" x 6"), Length 4.8 m x 9 | 44 | m | 3.4 | 149.6
Treated Batten 19 x 50mm | 33 | m | 1.31 | 43.31
MDF Primed Torus Architrave 44mm | 130 | m | 5.47 | 711.75
Sawn Timber Treated C16/C24 47 x 195mm | 60 | m | 4.54 | 272.25
MDF Window Board 25 x 244mm x 4.8m | 3 | each | 48.84 | 146.51
MDF Primed Torus Skirting 144mm | 155 | m | 5.31 | 823.44
Treated Batten 47 x 50mm | 39 | m | 4.11 | 160.39
Hardwood Plywood 2440 x 1220 x 18mm | 3 | sheet | 23.36 | 70.09
Insulation
Visqueen Vapour Check 500 GA Green 4 x 50m | 1 | roll | 150.16 | 150.16
25mm Celotex Insulation TB3025 Board 2400mm x 1200mm | 3 | each | 12.4 | 37.2
120mm Celotex Insulation XR4120 Board 2400mm x 1200mm | 43 | each | 38.75 | 1666.25
Kingspan Kooltherm K108 60mm | 206 | m2 | 28.2 | 5809.2
Aluminium Foil Tape 100mm x 45m | 23 | each | 9.36 | 215.34
Expanding Foam 750ml | 12 | each | 7.96 | 95.55
Knauf Earthwool Combi Cut 44 Loft Roll Insulation 100mm (13.89m²) | 6 | each | 40 | 240
Aluminium Foil Tape 50mm x 45m | 5 | each | 5.2 | 26
Knauf Earthwool Frametherm Insulation Slab 38 90mm (8m²) | 10 | each | 60.63 | 606.25
150mm Celotex Insulation XR4150 Board 2400mm x 1200mm | 54 | each | 47.5 | 2565
Knauf Earthwool Acoustic Partition Roll APR 35 100mm (11m²) | 1 | each | 75 | 75
Masonry
Solid Low Density Concrete Blocks 3.6N 100mm | 559 | each | 4.58 | 2557.43
Sika Maxmix Concentrated Plasticiser 1L | 5 | each | 13.96 | 69.81
Damp Proof Course 225mm x 30m | 4 | each | 10.41 | 41.65
London Brick Company Commons | 727 | each | 2.11 | 1535.79
Damp Proof Membrane 1200ga 4m x 3m (12m2) | 9 | each | 14.04 | 126.34
Expansion Joint Foam 100 x 10mm x 10m | 1 | each | 23.74 | 23.74
Celcon Standard Aerated Concrete Block 3.6N 100mm | 2613 | each | 2.88 | 7512.38
Bricks allowance | 12207 | each | 1.13 | 13732.88
Staifix Housing Wall Ties HRT4 250mm box of 250 | 4 | pack | 52.06 | 208.25
Wall Starter Kit Stainless Steel 2 x 1.2m | 4 | each | 14.57 | 58.3
Cavity Closer Double Flange 150mm x 2440mm | 28 | each | 15.6 | 436.8
Precast Concrete
Supreme Concrete Padstone 440mm x 215mm x 102mm | 8 | each | 28.81 | 230.5
Supreme Prestressed Concrete Lintel 65mm x 100mm x 2100mm | 4 | each | 19.51 | 78.05
Builders Metalwork
Heavy Restraint Strap 1000 x 30 x 5mm | 2 | each | 5.94 | 11.88
Heavy Restraint Strap 1200 x 30 x 5mm | 19 | each | 7.14 | 135.61
Standard Joist Hanger 100mm x 250mm JHA270/100 | 12 | each | 1.36 | 16.35
Standard Joist Hanger 44mm x 238mm JHA270/44 | 6 | each | 1.33 | 7.95
Fixings
No Nonsense General Purpose Silicone Clear 310ml | 12 | each | 4.99 | 59.85
Masonry Torx Frame Screw 7.5 x 82mm | 152 | each | 0.19 | 28.5
Galvanised Clout Nails 2.65 x 30mm 1kg Pack | 14 | kg | 10.41 | 145.78
Hex Nut M16 Zinc plated | 12 | each | 0.41 | 4.95
High Tensile Bolt M16 x 60mm | 12 | each | 0.65 | 7.8
Screws 5 x 80mm box of 100 | 11 | box | 5.51 | 60.64
Nylon Anchor Hammerfix Screws M6x60mm Box of 50 | 1 | box | 7.39 | 7.39
Screws 4.5 x 60mm box of 200 | 14 | box | 7.8 | 109.2
Screws 5 x 100mm box of 100 | 16 | box | 6.66 | 106.6
Brown Plastic Plugs Box of 100 | 2 | box | 4.58 | 9.15
Screws 4 x 50mm box of 200 | 2 | box | 4.47 | 8.95
75mm x 3.75 Galvanized Round Wire Nail 1kg Pack | 2 | pack | 6.96 | 13.93
50mm x 2.65 Galvanized Round Wire Nail 1kg Pack | 1 | pack | 7.69 | 7.69
20mm Extra Large Head Galvanised Clout Nail 1kg | 1 | pack | 7.49 | 7.49
White 40mm Plastic Headed Pins x 250 | 4 | box | 7.16 | 28.65
Square Twist Nails 3.7 x 30mm 1kg | 2 | pack | 6.86 | 13.73
Nylon Anchor Hammerfix Screws M5x50mm Box of 100 | 2 | box | 6.31 | 12.63
Oak 40mm Plastic Headed Pins x 250 | 1 | box | 7.19 | 7.19
65mm x 2.65 Galvanized Round Wire Nail 1kg Pack | 8 | pack | 7.06 | 56.5
Nylon Anchor Hammerfix Screws M6x80mm Box of 50 | 40 | box | 9.57 | 383
Pinkgrip Grab Adhesive 350ml | 41 | each | 4.16 | 170.66
MitreBond Aerosol kit 2Pcs | 11 | each | 10.4 | 114.4
51mm Paslode galvanised angled brads 16ga 2000 Pack | 7 | pack | 34.36 | 240.54
Rawplug Nylon Frame Fixings 8 x 100mm | 77 | each | 0.72 | 55.82
Metals
UC 203x203x46 | 40 | m | 83.75 | 3350
Angle Cleats 100 x 100 x 10mm | 4 | each | 8.13 | 32.5
Paints
Ronseal Refined Danish Oil 500ml | 37 | each | 12.8 | 473.6
Thermoguard W Intumescent Paint 2.5 Ltr | 11 | tin | 61.88 | 680.63
Steel Red Oxide Primer 750ml | 10 | tin | 8.11 | 81.13
Dulux Trade High Gloss Paint White 2.5Ltr | 20 | each | 36.46 | 729.25
Leyland Trade Acrylic Primer Undercoat White 2.5Ltr | 10 | each | 19.79 | 197.88
Dulux Trade Wood Primer Undercoat White 2.5Ltr | 7 | each | 48.96 | 342.74
Johnstones Primer White 2.5 Ltr | 2 | each | 36.45 | 72.9
Dulux Trade Matt Emulsion Paint White 10Ltr | 9 | each | 60.41 | 543.71
Dulux Trade Matt Emulsion Paint Magnolia 10Ltr | 6 | each | 64.59 | 387.52
Cuprinol Wood Preserver Clear 5 Ltr | 12 | tin | 47.9 | 574.8
Plasterboards
Gyproc Dry-Wall Adhesive 25kg | 72 | bag | 13.88 | 999
Thistle Multi Finish Plaster 25kg | 109 | bag | 9.78 | 1065.47
Drywall Scrim Tape 48mm x 90m | 17 | roll | 5.09 | 86.49
Kingspan K118 Kooltherm Insulated Plasterboard | 360 | m2 | 25.64 | 9229.5
Thin Coat Angle Bead 2.4m | 100 | each | 1.81 | 181.25
Standard Plasterboard SE 2400 x 1200 x 12.5mm | 95 | sheet | 14.11 | 1340.69
Drywall Screws 38mm Box of 1000 | 6 | box | 13.54 | 81.23
Drywall Screws 65mm Box of 500 | 6 | box | 14.57 | 87.45
Thin Coat Angle Bead 3m | 70 | each | 2.09 | 146.13
Standard Plasterboard TE 2400 x 1200 x 12.5mm | 26 | sheet | 14.11 | 366.93
Wall Finishes
Softwood Shiplap Cladding 12 x 121 x 2400mm | 55 | each | 4.25 | 233.75
Exterior Screws C2 40mm box of 350 | 5 | box | 14.44 | 72.19
Timber Cladding allowance | 65 | m2 | 50 | 3250
Drainage
Circular Plastic Cover & Frame Ø450mm | 2 | each | 25.74 | 51.48
Manhole Riser Ø450mm x 235 mm (H) | 4 | each | 42.66 | 170.65
5 Inlets Inspection Chamber Base Ø450mm x 290mm (H) | 2 | each | 45.69 | 91.38
Underground Pipe 3m - Single Socket 110mm | 10 | each | 16.8 | 168
Back Inlet Bottle Gully-Round | 5 | each | 37.91 | 189.56
Rodding Points Square Spigot 110mm | 2 | each | 34.36 | 68.72
Underground Pipe 3m - Plain Ended 110mm | 10 | each | 15.82 | 158.25
Pipe Coupling Double Socket 110mm | 10 | each | 5.4 | 54
Adjustable Bend 110mm | 5 | each | 18.63 | 93.13
Galvanised Top Domestic Channel Drain x 1m | 6 | each | 12.7 | 76.2
Single Socket Soil Pipe Black 3m x 110mm | 1 | each | 21.72 | 21.72
Plain End Soil Pipe Black 3m x 110mm | 1 | each | 25.26 | 25.26
Single Socket Access Pipe Black - 110mm | 1 | each | 22.91 | 22.91
Pipe Clip Black - 110mm | 3 | each | 2.16 | 6.49
Weathering Collar Black - 110mm | 1 | each | 4.63 | 4.63
92.5° Bend Double Socket Black - 110mm | 1 | each | 14.46 | 14.46
Rubber Boss Adaptor 32mm | 1 | each | 2.09 | 2.09
Rubber Boss Adaptor 40mm | 1 | each | 2.34 | 2.34
Strap Boss Black 32,40mm - 110mm | 2 | each | 6.91 | 13.83
Soakaway Crate 1.0 x 0.5 x 0.4m | 11 | each | 41.19 | 453.06
Half Round Fascia Bracket - Black | 52 | each | 0.88 | 45.5
Half Round External Stop End - Black | 10 | each | 1.85 | 18.5
Half Round Running Outlet - Black | 6 | each | 3.79 | 22.73
Half Round Union Bracket - Black | 17 | each | 2.59 | 43.99
Round Downpipe 2.5 m lengths 68mm - Black | 8 | each | 10.11 | 80.9
Round Shoe 68 mm - Black | 6 | each | 3.94 | 23.63
Half Round Clip 68 mm - Black | 26 | each | 0.98 | 25.35
Round Bend 92.5° Black 68 mm | 8 | each | 3.38 | 27
Half Round Gutter 3 m length - Black | 15 | each | 7.18 | 107.63
Round Socket 68 mm Black | 6 | each | 1.96 | 11.78
Round Bend 112.5° Black 68 mm | 4 | each | 3.38 | 13.5
Heating
RM Prostel Unvented Direct Cylinder 300L | 1 | each | 721.85 | 721.85
Heatmiser Touch-W | 5 | each | 63.32 | 316.63
ProWarm™ Standard Output - 87m2 | 1 | each | 1093.74 | 1093.74
Plastics
uPVC White Solid Soffit Board 9 x 250mm x 5m | 11 | each | 41.49 | 456.36
uPVC White Fascia Board 18 x 200mm x 5m | 17 | each | 54.45 | 925.65
White External Corner 500mm | 9 | each | 4.88 | 43.88
White External Corner 300mm | 8 | each | 2.19 | 17.5
White Fascia Joiner | 1 | each | 5.2 | 5.2
uPVC White Vented Soffit Board 9 x 400mm x 2.5m | 14 | each | 41.51 | 581.17
uPVC White Fascia Board 18 x 400mm x 5m | 1 | each | 123.84 | 123.84
Kitchen / Bathroom
Kitchen allowance | 1 | each | 8750 | 8750
Cooker / Hob supplied by client | 1 | each | 0 | 0
Oven supplied by client | 1 | each | 0 | 0
Extractor Hood supplied by client | 1 | each | 0 | 0
Other
Regular Diesel | 406 | l | 2.38 | 964.25
Sign Boards | 1 | each | 125 | 125
Subtotal |  |  |  | 177723.73

## Plant and Tools
Plant & Tool
Description | Quantity | Term | Unit | Rate | Total
Access
Provide Scaffolding for 8 weeks, Height - 4.8m, Width - 55m | 1 | 1 | each | 9504 | 9504
Dumpers
1 Tonne Skip Loader | 1 | 1 | day | 75 | 75
1 Tonne Skip Loader | 1 | 1 | day | 75 | 75
1 Tonne Skip Loader | 1 | 1 | day | 75 | 75
1 Tonne Skip Loader | 1 | 1 | day | 75 | 75
1 Tonne Skip Loader | 1 | 1 | day | 75 | 75
1 Tonne Skip Loader | 1 | 1 | day | 75 | 75
1 Tonne Skip Loader | 1 | 1 | day | 75 | 75
1 Tonne Skip Loader | 1 | 1 | day | 75 | 75
1 Tonne Skip Loader | 1 | 1 | day | 75 | 75
1 Tonne Skip Loader | 1 | 1 | day | 75 | 75
Excavators
1.5 Tonne Excavator | 1 | 4 | day | 60.16 | 240.63
1.5 Tonne Excavator | 1 | 5 | day | 48.13 | 240.63
1.5 Tonne Excavator | 1 | 1 | day | 68.75 | 68.75
1.5 Tonne Excavator | 1 | 4 | day | 60.16 | 240.63
1.5 Tonne Excavator | 1 | 3 | day | 80.21 | 240.63
Post Hole Auger Digger Attachment 6, 9 & 12" | 1 | 3 | day | 72.92 | 218.75
Gardening
Rotavator Hydraulica | 1 | 1 | day | 68.75 | 68.75
Skips
2 Yard Skip 1.2m(L) x 0.61(W) x 0.76(H) | 1 | - | each | 135 | 135
6 Yard Skip 2.6m(L) x 1.5(W) x 1.2(H) | 1 | - | each | 247.5 | 247.5
Rubble Sack 30kg | 22 | 1 | each | 4.38 | 96.25
4 Yard Skip 1.8m(L) x 1.3(W) x 1.0(H) | 1 | - | each | 190 | 190
8 Yard Skip 3.6m(L) x 1.7(W) x 1.2(H) | 6 | - | each | 318.75 | 1912.5
8 Yard Skip 3.6m(L) x 1.7(W) x 1.2(H) | 7 | - | each | 318.75 | 2231.25
8 Yard Skip 3.6m(L) x 1.7(W) x 1.2(H) | 2 | - | each | 318.75 | 637.5
8 Yard Skip 3.6m(L) x 1.7(W) x 1.2(H) | 10 | - | each | 318.75 | 3187.5
8 Yard Skip 3.6m(L) x 1.7(W) x 1.2(H) | 7 | - | each | 318.75 | 2231.25
8 Yard Skip 3.6m(L) x 1.7(W) x 1.2(H) | 6 | - | each | 318.75 | 1912.5
8 Yard Skip 3.6m(L) x 1.7(W) x 1.2(H) | 1 | - | each | 318.75 | 318.75
8 Yard Skip 3.6m(L) x 1.7(W) x 1.2(H) | 1 | - | each | 318.75 | 318.75
Portable Toilet
Portable Toilet 5ft x 4ft | 1 | 30 | week | 37.5 | 1125
Container
Steel Container 8ft x 8ft | 1 | 30 | week | 26.25 | 787.5
Fencing & Barriers
Delivery and Collection Cost | 1 | - | each | 56.25 | 56.25
Delivery and Collection Cost | 1 | - | each | 56.25 | 56.25
Delivery and Collection Cost | 1 | - | each | 56.25 | 56.25
Delivery cost | 1 | - | each | 81.25 | 81.25
Delivery and Collection Cost | 1 | - | each | 56.25 | 56.25
Heras Fence Panel Standard 3.5m x 2m | 29 | 30 | week | 8.5 | 7395
Pedestrian Gate For 1.1m Heras Fence | 1 | 30 | week | 6.13 | 183.75
Vehicle Gate 4.2m - Heras Fence | 1 | 30 | week | 38.25 | 1147.5
Delivery and Collection Cost | 1 | - | each | 350 | 350
Delivery and Collection Cost | 1 | - | each | 56.25 | 56.25
Delivery and Collection Cost | 1 | - | each | 56.25 | 56.25
Subtotal |  |  |  |  | 36399.02

## Other costs
Other costs
Description | Quantity | Unit | Rate | Total
Lump sum
Preliminaries
Safety, First Aid, Protective clothings | 1 | each | 337.5 | 337.5
Subtotal |  |  |  | 337.5

## Profit
Profits: Total
Description | Costs | Revenue | Profit
Site Work
Site Work | 31830 | 39812 | 7982
General Preliminaries | 9140 | 11450 | 2310
Fences and Barriers | 7330 | 9163 | 1833
Site Equipment | 1855 | 2319 | 464
Demolition / Removal | 5901 | 7376 | 1475
Scaffolding | 7603 | 9504 | 1901
Site Drainage
Site Drainage | 5054 | 6318 | 1264
SVP | 169 | 211 | 42
Surface Water Manhole | 853 | 1066 | 213
Surface Water Drainage run | 2270 | 2838 | 568
Aco Channels | 785 | 981 | 196
Soakaway | 977 | 1222 | 244
Substructure
Substructure | 27487 | 34358 | 6872
Strip Foundation | 4829 | 6037 | 1207
Trench Foundation (Historic Septic Tank Area) | 1918 | 2397 | 479
Cavity Walls Below DPC | 6067 | 7583 | 1517
Concrete Floor | 14673 | 18341 | 3668
Structure
Structure | 127208 | 159010 | 31802
Cavity Wall | 42624 | 53280 | 10656
Block Wall | 6805 | 8506 | 1701
Timber Stud Wall | 8149 | 10186 | 2037
Window Type 1 | 688 | 860 | 172
Window Type 2 | 431 | 539 | 108
Window Type 3 | 404 | 505 | 101
Window Type 4 | 523 | 654 | 131
Window Type 5 | 1164 | 1455 | 291
Window Type 6 | 832 | 1040 | 208
Window Type 7 | 482 | 603 | 121
Window Type 8 | 457 | 572 | 114
Window Type 9 | 441 | 552 | 110
Bifold Door | 4718 | 5898 | 1180
Composite Door | 966 | 1208 | 242
Wooden Door | 1483 | 1854 | 371
Universal Column | 3342 | 4177 | 835
Connection | 260 | 325 | 65
Floor | 6797 | 8497 | 1699
Apex Roof (Main Roof) | 3063 | 3829 | 766
Apex Roof (Storage Area) | 1628 | 2035 | 407
Flat Roof | 7522 | 9402 | 1880
Slate Range | 19767 | 24708 | 4942
Pitched Roof Windows | 2688 | 3360 | 672
Rafters Insulation | 3731 | 4664 | 933
Upvc | 3492 | 4365 | 873
Rainwater Goods | 777 | 971 | 194
Universal Column (Ridge Beam) | 1988 | 2484 | 497
Universal Column (Dormer Beam) | 1988 | 2484 | 497
Services
Services | 31108 | 38885 | 7777
Electrics | 11114 | 13893 | 2779
En Suite 1 Plumbing | 1977 | 2471 | 494
En Suite 2 Plumbing | 1977 | 2471 | 494
Bathroom Plumbing | 1931 | 2413 | 483
Kitchen Plumbing | 1103 | 1379 | 276
Heating | 13006 | 16257 | 3251
Finishes
Finishes | 48673 | 60841 | 12168
Plasterboard on battens | 9272 | 11590 | 2318
Plasterboard on battens (GF Ceiling) | 3218 | 4022 | 804
Decorating | 4090 | 5113 | 1023
Timber Cladding | 6999 | 8749 | 1750
Kitchen | 8740 | 10925 | 2185
Single Door (FF) | 1201 | 1501 | 300
Double Door (FF) | 1003 | 1254 | 251
Single Pocket Door (FF) | 1717 | 2147 | 429
Double Sliding Door (FF) | 2098 | 2623 | 525
Single Door (FF) | 1201 | 1501 | 300
Double Door (GF) | 998 | 1247 | 249
Double Folding Door (GF) | 1189 | 1486 | 297
Staircase | 1534 | 1917 | 383
Balustrade | 1318 | 1647 | 329
Skirting Board | 3107 | 3884 | 777
Window Board | 448 | 560 | 112
Boxing | 540 | 675 | 135
Landscaping
Landscaping | 27428 | 34286 | 6857
Resin | 15189 | 18987 | 3797
Fence | 10129 | 12662 | 2532
Turf | 2110 | 2638 | 528
Subtotal |  |  | 149443